## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 100
| Number of testers | 5
| Test cycle duration | 5 days
Status for 08/31/2013
| Number of test cases planned | 20 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 18
| Number of test cases executed overall | 78
| Number of defects encountered today | 2
| Number of defect encountered so far | 10
| Number of critical defects- still open | 3
Overall status
| Number of test cases planned | 100
| Number of test cases executed | 78
| Pass Percentage of the defects | 98%
| Defects density | 2.5 per day
| Critical defects percentage | 20%
©- SoftwareTestingHelp.com

## Detailed status
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin | Login Page | Login | Medium | Tester A | 2013-08-31 | Pass
Admin | Country Management | Add country | Complex | Tester B | 2013-08-31 | Pass
|  | Delete country | Complex | Tester B | 2013-08-31 | Pass
|  | Verify the list display | Medium | Tester B | 2013-08-31 | Pass
Admin | City management | Add City | Complex | Tester A | 2013-08-31 | Pass
|  | Delete City | Complex | Tester A | 2013-08-31 | Pass
|  | Verify the list display | Medium | Tester A | 2013-08-31 | Pass
Admin | Car Make Management | Add Car Make | Complex | Tester B | 2013-08-31 | Fail | 1028: Cannot add car make, 404 error on clicking the link | 1- High | Open
|  | Delete car make | Complex | Tester B | 2013-08-31 | Blocked | 1028
|  | Verify the list display | Medium | Tester B | 2013-08-31 | Pass
Admin | Car Model Management | Add Car Model | Complex | Tester X | 2013-08-31 | Pass
|  | Delete car model | Complex | Tester X | 2013-08-31 | Pass
|  | Verify the list display | Medium | Tester X | 2013-08-31 | Fail | 1029: List not displayed. Table contents empty always | 2- Medium | Assigned
Admin | Featured car | Select all | Medium | Tester X | 2013-09-01 | Not executed
|  | Select New | Complex | Tester X | 2013-08-31 | Pass
|  | deselect some | Complex | Tester X | 2013-08-31 | Pass
|  | deselect all | Medium | Tester A | 2013-09-01 | Not executed
©- SoftwareTestingHelp.com

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
1028 | Cannot add car make, 404 error on clicking the link | 1. Login to the site using the admin credentials 2. Click on the "Car Make Management" menu option from the left side navigation 3. The list of the makes of the cars available will be displayed 4. There will also be a link "Add new car make" present on the top(header) of the list 5. Click on the link Expected result: The page where the admin can enter a new make for the car should be displayed Actual Result: A 404 error causes the system to crash. The site has to be relaunched to recover from this state. | 1- High | Open | Tester X | Dev representative
©- SoftwareTestingHelp.com