## Summary
Test Summary Report: Metrics Dashboard
ShopEasy Checkout Redesign ¦ Release 3.2 (build 3.2.0-rc4) ¦ System Test ¦ Sample data. Overwrite the blue cells on the other sheets and this page updates.
Created by softwaretestinghelp.com
Metric | Value | Note
EXECUTION
Planned test cases | 500 | Total in the approved plan
Executed (Passed + Failed) | 476
Passed | 443
Failed | 33
Blocked | 13 | Cannot run: defect, environment or data
Not run | 11 | Planned but not yet executed
% Executed | 95.2% | Executed / Planned
% Passed (of executed) | 93.07% | Passed / Executed
% Passed (of planned) | 88.6% | Passed / Planned
% Blocked | 2.6% | Blocked / Planned
Automation coverage | 36% | Automated / Planned
DEFECTS
Total valid defects | 35
Open defects | 10
Open Critical | 1
Open High | 3
Closure rate | 60% | Closed / total valid
Defect density (per KLOC) | 1.4286 | Valid defects / KLOC
COVERAGE
Requirements coverage | 95.83% | Requirements with at least one test
Requirements verified | 83.33% | Requirements with all tests passed
Statement coverage (unit tests) | 78%
EXIT CRITERIA
Criteria met | 4
Criteria not met | 3
Suggested status | AMBER/RED: 3 of 7 criteria not met | Confirm using judgement; see Exit Criteria sheet

## Execution
Test Execution Metrics
Enter Planned, Passed, Failed, Blocked and Not Run per module (blue cells). Everything else calculates. To add a module, insert a row above the last module row and copy the formulas down.
Module / Feature | Planned | Passed | Failed | Blocked | Not Run | Executed (Passed+Failed) | % Executed | % Passed (of executed) | % Passed (of planned) | % Failed (of executed) | % Blocked (of planned) | Check
Login and Registration | 60 | 57 | 3 | 0 | 0 | 60 | 100% | 95% | 95% | 5% | 0% | OK
Product Search and Catalog | 85 | 78 | 5 | 0 | 2 | 83 | 97.65% | 93.98% | 91.76% | 6.024% | 0% | OK
Cart and Wishlist | 70 | 63 | 4 | 2 | 1 | 67 | 95.71% | 94.03% | 90% | 5.97% | 2.857% | OK
Checkout and Payments | 120 | 98 | 12 | 6 | 4 | 110 | 91.67% | 89.09% | 81.67% | 10.91% | 5% | OK
Order Management | 65 | 58 | 4 | 2 | 1 | 62 | 95.38% | 93.55% | 89.23% | 6.452% | 3.077% | OK
Notifications | 40 | 36 | 2 | 0 | 2 | 38 | 95% | 94.74% | 90% | 5.263% | 0% | OK
Admin Portal | 60 | 53 | 3 | 3 | 1 | 56 | 93.33% | 94.64% | 88.33% | 5.357% | 5% | OK
TOTAL | 500 | 443 | 33 | 13 | 11 | 476 | 95.2% | 93.07% | 88.6% | 6.933% | 2.6% | OK
Automation
Automated test cases | 180
Automation coverage (% of planned) | 36%
Automated tests passed | 175
Automated pass rate | 97.22%
Rules: Planned = Passed + Failed + Blocked + Not Run. Executed = Passed + Failed. The Check column shows CHECK if a row does not reconcile.

## Defects
Defect Metrics
Enter counts of valid defects (blue cells). Rejected and duplicate items are entered separately and are excluded from all counts.
Severity | Open | Fixed / Retest Pending | Closed | Total | % of total
Critical | 1 | 0 | 2 | 3 | 8.571%
High | 3 | 1 | 5 | 9 | 25.71%
Medium | 4 | 2 | 9 | 15 | 42.86%
Low | 2 | 1 | 5 | 8 | 22.86%
TOTAL | 10 | 4 | 21 | 35 | 100%
Defect metrics
Metric | Value | Basis
Size of new and changed code (KLOC) | 24.5 | Input. Use function points or another size measure if you prefer, and change the label.
Rejected / duplicate defects (excluded) | 6 | Input. Not counted in the totals above.
Defect density per KLOC | 1.4286 | Valid defects / KLOC
Defects per 100 executed tests | 7.3529 | Valid defects / executed tests x 100
Closure rate | 60% | Closed / total valid defects
Resolved rate (closed + fixed) | 71.43% | (Fixed + Closed) / total valid defects
Open Critical + High defects | 4 | Open defects only
Rejection rate | 14.63% | Rejected / (valid + rejected). A high value points to unclear requirements.
Defects by module
Module | Defects | % of total | Defects per 100 executed tests
Login and Registration | 3 | 8.571% | 5
Product Search and Catalog | 4 | 11.43% | 4.8193
Cart and Wishlist | 4 | 11.43% | 5.9701
Checkout and Payments | 12 | 34.29% | 10.9091
Order Management | 5 | 14.29% | 8.0645
Notifications | 3 | 8.571% | 7.8947
Admin Portal | 4 | 11.43% | 7.1429
TOTAL | 35 | 100% | 7.3529
Weekly defect trend
Week | Opened | Resolved (fixed or closed) | Open backlog (cumulative)
Wk 1 (24 Aug) | 9 | 2 | 7
Wk 2 (31 Aug) | 14 | 6 | 15
Wk 3 (7 Sep) | 8 | 9 | 14
Wk 4 (14 Sep) | 4 | 8 | 10
TOTAL | 35 | 25 | 10
Reconciliation checks
Module total = severity total | OK
Weekly opened = severity total | OK
Final backlog = open defects | OK

## Coverage
Coverage Metrics
Requirements coverage comes from your Requirements Traceability Matrix (RTM). Enter counts per module (blue cells).
Module | Requirements in scope | Covered (>= 1 test) | Fully verified (all tests passed) | Uncovered | % Covered | % Verified
Login and Registration | 6 | 6 | 6 | 0 | 100% | 100%
Product Search and Catalog | 8 | 8 | 7 | 0 | 100% | 87.5%
Cart and Wishlist | 7 | 7 | 6 | 0 | 100% | 85.71%
Checkout and Payments | 12 | 11 | 8 | 1 | 91.67% | 66.67%
Order Management | 6 | 6 | 5 | 0 | 100% | 83.33%
Notifications | 4 | 4 | 4 | 0 | 100% | 100%
Admin Portal | 5 | 4 | 4 | 1 | 80% | 80%
TOTAL | 48 | 46 | 40 | 2 | 95.83% | 83.33%
Other coverage measures
Statement coverage (unit tests) | 78%
Branch coverage (unit tests) | 69%
Automation coverage (% of planned tests) | 36%
Source of code-coverage figures | SonarQube, build 3.2.0-rc4
Uncovered requirements and reasons
REQ-CHK-11 (gift-card payments): deferred to Release 3.3 (CR-217).
REQ-ADM-05 (bulk product import): test data not available; will run in the regression cycle.
Covered means a requirement has at least one mapped test. Verified is stricter: every mapped test has passed.

## Exit Criteria
Exit Criteria Evaluation
Copy the criteria and targets from your approved Test Plan (blue cells). Actual values link to the other sheets. Status calculates automatically.
Criterion | Operator | Target | Actual | Status | Comment
Planned tests executed | >= | 100% | 95.2% | NOT MET | 24 tests not executed (13 blocked, 11 not run)
Pass rate of executed tests | >= | 90% | 93.07% | MET | Checkout at 89.1% is below target on its own
Open Critical defects | <= | 0 | 1 | NOT MET | DEF-1042
Open High defects | <= | 2 | 3 | NOT MET | DEF-1038, DEF-1047, DEF-1051
Blocked tests (% of planned) | <= | 5% | 2.6% | MET | 13 of 500
Requirements coverage | >= | 95% | 95.83% | MET | 2 requirements uncovered
Checkout p95 response time (seconds) | <= | 3 | 2.4 | MET | 2,000 concurrent users, 60 minutes (JMeter). Enter your measured value.
Criteria met | 4
Criteria not met | 3
Suggested status | AMBER/RED: 3 of 7 criteria not met
The suggested status is a starting point only. Choose Amber or Red by judging whether a credible recovery plan exists, then record the release decision in the report.

## Definitions
Metric Definitions and How to Use This Workbook
Metric | Formula | What it tells you
Planned tests | Passed + Failed + Blocked + Not Run | Total tests in the approved plan for this cycle.
Executed tests | Passed + Failed | Tests actually run to a result. Blocked and Not Run are excluded.
% Executed | Executed / Planned | Progress against plan.
% Passed (of executed) | Passed / Executed | Quality of what was actually tested.
% Passed (of planned) | Passed / Planned | Stricter view: tests not yet executed count against you.
% Failed | Failed / Executed | Share of executed tests that found a problem.
% Blocked | Blocked / Planned | Testing held up by defects, environment or data. Above 5% usually needs escalation.
Automation coverage | Automated tests / Planned tests | How much of the suite is automated.
Requirements coverage | Requirements with >= 1 test / Total requirements | Whether every requirement has been tested at all.
Requirements verified | Requirements with all tests passed / Total requirements | Whether every requirement has been proven to work.
Defect density | Valid defects / KLOC (or per 100 executed tests) | Relative quality; compare releases using the same basis.
Closure rate | Closed defects / Total valid defects | How much of the defect backlog is finished.
Rejection rate | Rejected / (Valid + Rejected) | Quality of requirements and test cases.
Open backlog | Cumulative (Opened - Resolved) | Trend: falling backlog suggests stabilization.
Colour legend
Blue text, yellow fill | Input: type or paste your own value here.
Black text | Formula: do not overwrite.
Green text | Link to another sheet: do not overwrite.
Sample data: the workbook is pre-filled with the fictional ShopEasy Release 3.2 example from Test_Summary_Report_Example.pdf. Overwrite the blue cells with your own numbers.